## Action Items
APPENDIX B: FIRST TIER PLANNING INFORMATION ACTION ITEMS AND SCHEDULE
First Tier Planning Committee: Kathy Parsons, Liz Craig, Mary Catherine Martin, Lindsay Addison, Ruth Boettcher, Caleb Spiegel, and back-up member Kate Goodenough
TOPIC/ISSUE | ACTION ITEM | RESPONSIBLE INDIVIDUAL(S)/ORGANIZATION | TIMELINE, DEADLINE OR DUE DATE | DOES THIS ACTION ITEM REQUIRE FUNDING? | DATE COMPLETED | COMMENTS
Topic 1, Issue A | Item 1: Send Workshop attendees the Atlantic Flyway Council recommendations supporting coordinated Atlantic flyway CWB surveys and the development of a CWB data management system | Ruth Boettcher | Nov. 27, 2019 | No | Jan. 9, 2020 | Uploaded doc on SCAW-WG website on the 2023 CWB survey planning page
Topic 1, Issue C | Item 2: Put First Tier planning information documents, reports and spreadsheets needed to complete Items 7 - 9 on SCAW-WG website and provide link to the First Tier Planning Committee | Ruth Boettcher and Amanda Hackney | Nov. 27, 2019 | No | Jan. 9, 2020 | Uploaded docs on SCAW-WG website on the 2023 CWB survey planning page
N/A | Item 3: Complete version 3 of the on-line questionnaire that includes recommendations from the Workshop attendees and send to individuals who volunteered to review. | Ruth Boettcher | Dec. 1, 2019 | No | Jan. 3, 2020 | Sent to reviewers with a Jan. 15th deadline.
N/A | Item 4: Send an email to state, provincial and federal POCs stating they will be receiving an on-line CWB questionnaire in early January that needs to be completed with all their CWB partners in the same room By Februray 15, 2020. | Ruth Boettcher | Dec. 1, 2019 | No | Jan. 10, 2020 | A follow-up email will be sent around mid-December that states the exact date when the questionnaire will be sent in January.
N/A | Item 5: Complete review of the on-line questionnaire | Kate Goodenough, Mary-Catherine Martin, Fletcher Smith, Dave Brinker, Carmen Johnson, Rob Longiaru, Lindsay Addison, Lisa Ferguson, Kashi Davis, Rachael Pierce | Jan. 15, 2020 | No
N/A | Item 6: Make revisions to the on-line questionnaire and send final version to state, provincial and federal POCs along with an email stating by when the questionnaire needs to be completed. | Ruth Boettcher | Jan. 31, 2020 | No |  | States, provinces and federal partners will be asked to have the questionnaire completed by Mar. 31, 2020.
Topic 1, Issue C | Item 7: Examine SWAPS, MANEM Plan, ACAD, BCC, Waterbird step-down plans, relevant provincial bird plans and priority CWB species that breed in Atlantic Canada to develop a First Tier list of priority survey species. | First Tier Planning Committee | Feb. 15, 2020 | No |  | Committee members will work with SCAW-WG regional sub-groups in this information gathering effort. Sub-group leads contact information is provided on sheet entitled SCAW-WG Sub-group Leads.
Topic 1, Issue E | Item 8: Compile a list of CWB survey methods currently deployed by states, provinces and federal partners | First Tier Planning Committee | Mar. 30, 2020 | No |  | Committee will work with SCAW-WG regional sub-group leads to obtain this information from states, provinces and federal partners. Sub-group leads contact information is provided on sheet entitled Sub-group Leads.
Topic 1, Issue H | Item 9: Conduct literature search of existing survey methods, especially for difficult-to-survey CWBs | First Tier Planning Committee | Mar. 30, 2020 | No |  | On-line questionnaire will help identify priority difficult-to-survey CWB species
Topic 3, Issue B | Item 10: Contact Sara Schweitzer to discuss potential NABCI's role in the planning and/or support for the 2023 survey. | Ruth Boettcher | Jan. 15, 2020 | No
Topic 3, Issue B | Item 11: Find out how much VA (or each Atlantic state/province) contributes to the Atlantic Flyway Council. | Ruth Boettcher | Feb. 1, 2020 | No |  | Ask Gray Anderson or Becky Gwen. Spoke to Gray Anderson on Dec. 3, 2019 and he said money is available for NGTS projects and intiatives. He encourages the submittal of proposals related to the 2023 CWB survey and CWB data mangt. He is not sure how much each state contributes to the AFC; will talk to Becky about this.
Topic 3, Issue B | Item 12: Find out how the Atlantic Flyway Council deseminates funds to projects/initiatives. | Ruth Boettcher | Feb. 1, 2020 | No |  | Ask Gwen Brewer, Atlantic Flyway NGTS coordinator
Topic 1, Issue A | Item 13: Contact representatives from the MS Flyway Council (David Hanni, NGTS member; Andrew Forbes, USFWS Liaison; Bill Vermillion, Gulf Coast Joint Venture; Sumner Matteson, NGTS Chair) and the Atlantic Flyway Council (Gwen Brewer, NGTS Chair; Andrew Vitz, Waterbird Committee Chair: and Caleb Spiegel, USFWS Liaison; to begin coordinated efforts to gain state buy-in for future coordinated CWB surveys across Atlantic and MS flyways | Ruth Boettcher | Jan. 15, 2020 | No
Topic 1, Issue A | Item 14: Pose geographic scope questions at the February 2020 MS Flyway meeting to get a sense of the level of interest among Gulf coast states to participate in the 2023 survey and to convey the benefits that can be derived from obtaining large scale population estimates, trends, and distributions | A member of the MS Flyway Nongame Technical Section (NGTS) – TBD | Feb. 25-28, 2020 | No
Topic 1, Issue B | Item 15: Pose geographic coverage questions at the February 2020 Atlantic and MS Flyway meetings to get a sense of current coastal and inland coverage and their capacity to include inland colonies in the 2023 survey effort. | Caleb Spiegel, Ruth Boettcher and a member of the MS Flyway NGTS -TBD | Feb. 20-28, 2020 | No
Topic 2, Issue C | Item 16: Ask John Alexander to record an informational webinar about the Avian Knowledge Network with a focus on the CWB platform | Ruth Boettcher | Dec. 1, 2019 | Yes | Jan. 6, 2020 | John agreed to do put together a webinar; he requested a contribution of roughly $2,500 to help defer costs. If this is not doable, he will prepare the webinar anyway. Also discussed preparing AKN CWB platform development proposals for the upcoming Atlantic and MS flyway Council winter meetings.
Topic 3, Issue B | Item 17: Examine what other competitive State Wildlife Grant proposals are being developed for potential integration into the planning and/or implementation of the 2023 survey. | First Tier Planning Committee | 2020-06-01 | No
Topic 1, Issue E and Topic 1, Issue F | Item 18: Hire a statistician (student, consultant, post-doc, etc.) early in the planning process to help with issue of survey metric and methods | TBD | ~Dec. 2020 | A funding source needs to identified |  | FMS recommended Jim Lyons, Conor McGowan and Elizabeth Hunter
Topic 1, Issue H and Topic 3, Issue A | Item 19: Obtain guidance from state and provinces that survey difficult-to-survey species on methods and/or to borrow additional resources (e.g., staff, equipment) necessary for surveying those species. | SCAW-WG regional sub-group leads | Dec. 2021 | No
Topic 1, Issue F and Topic 2, Issue C | Item 20: Establish and maintain a registry of CWB survey participants, by state, province and federal partnering agencies. | Ruth Boettcher and John Alexander | 2021 | Unk |  | The initial list can be obtained by way of the on-line questionnaire, which can hopefully get uploaded into the CWB data management system and managed from there.
Topic 2, Issue C | Item 21: Prepare a list of state and provincial databases. | TBD | 2021 | No |  | Explore the contents of the USGS CWBD at https://visualizebirds.shinyapps.io/shinyApp/.

## SCAW-WG Sub-group Leads
SCAW-WG Regional Sub-group | Geographic Extent | Co-lead's Names | Co-lead's Affiliations | Co-lead's Email Adresses
Gulf of Maine | Atlantic Canada - MA | Kathy Parsons | MASS Audubon | kparsons@massaudubon.org
|  | Elizabeth Craig | University of New Hampshire - Shoals Marine Lab. | ecc79@cornell.edu
|  | Linda Welch | USFWS - Maine Coastal Islands National Wildlife Refuge | linda_welch@fws.gov
|  | Sabina Wilhelm | Canadian Wildlife Service | sabina.wilhelm@canada.ca
Lower Northeast | RI - NY | Susan Elbin | New York City Audubon | selbin@nycaudubon.org
Mid-Atlantic | NJ - VA | Ruth Boettcher | VA Dept. of Game and Inland Fisheries | ruth.boettcher@dgif.virginia.gov
|  | Lisa Ferguson | Wetlands Institute | lferguson@wetlandsinstitute.org
|  | Dave Brinker | MD DNR - Natural heritage Program | dave.brinker@maryland.gov
Southeast | NC - Atlantic FL | Felicia Sanders | SC DNR | SandersF@dnr.sc.gov
|  | Tim Keyes | GA DNR | Tim.Keyes@dnr.ga.gov
|  | Walker Golder | National Audubon | WGOLDER@audubon.org
Gulf of Mexico | Gulf coast of FL - MEX | Owen Fitzsimmions | Coastal Bend Bays & Estuaries Program - Coastal Bird Program | owen@cbbep.org
|  | Jeffrey Gleason | USFWS - Gulf Restoration Program | Jeffrey_Gleason@fws.gov
|  | Amanda Hackney | GIS Consultant, Black Cat GIS and Biological Services | a.hackney@blackcatgis.com
|  | Kacy Ray | American Bird Conservancy -Coastal Birds, Program Manager | kray@abcbirds.org
|  | David Newstead | Coastal Bend Bays & Estuaries Program | dnewstead@cbbep.org